## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | Group J
Group Member: | Yuchen Wu |  | Progress Classes: | Ahead
Group Member: | Runsheng Gao |  |  | On-track
Group Member: | Lakindu Dissanayake |  |  | Behind
Group Member: | Jessica Bath |  |  | Way Behind
Tutor: | Dale
Class: | Wednesday 8.30
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Yuchen Wu | Runsheng Gao | Lakindu Dissanayake | Jessica Bath
|  |  | Group Formed |  | Weekly Contribution | Created github repo | Joined github
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Yuchen Wu | Runsheng Gao | Lakindu Dissanayake | Jessica Bath
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | 1.Designed some ADT and whole 2.Implemented MainMenu.h without error handling 3.Implemented LinkedList.h | Implemented player settings
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues | Cannot contact to James McClure
|  |  | Main menu |  | Other Notes | Formed a new group by Ruwan
User Prompt (for gameplay), but no/minimal error checking
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Yuchen Wu | Runsheng Gao | Lakindu Dissanayake | Jessica Bath
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | 1. Finished implementing Board, TileBag and Hand. They work properly. 2. Finished newGame() function, along with all user prompt. The game logic is 90% done. 3. Single round finished. | 1. Changed the method of readFromFile 2. Helped Yuchen finished switch player
|  |  | Initialisation of data strctures for new game |  | Issues | No contact/reply from Lakindu, hence reported to Dale.
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Yuchen Wu | Runsheng Gao | Lakindu Dissanayake | Jessica Bath
|  |  | Fully complete implementation and error free |  | Weekly Contribution | 1.finished score calculation function 2.finished save game and load game 3.wrote some test cases 4.fixed fatal bugs in gameplay logic, added a lot of user input checking. | 1. Finished calculatePlayerScore 2. Wrote some test cases
|  |  | Full error checking of user prompt |  | Issues | Got message from Lakindu and add him back to group
[5 empty] | Other Notes | Had a weekly meeting with Jessica and Runsheng
Final Tests
Group Report Written
|  | Progress | On-track